## Month-by-month
OPR-0006 QEF3 Timeline
Operational Document
Version no. 4 / Date of Publication 15.09.2026
Responsible staff member: Executive Director
Reviewed: Annually
Board approval: N/A
WHO | Apr.24 | May.24 | Jun.24 | Jul.24 | Aug.24 | Sep.24 |  | Oct.24 | Nov.24 | Dec.24 | Jan.25 | Feb.25 | Mar.25 | Apr.25 | May.25 | Jun.25 | Jul.25 | Aug.25 | Sep.25 | Oct.25 | Nov.25 | Dec.25 | Jan.26 |  | Feb.26 | Mar.26 | Apr.26 | May.26 | Jun.26 | Jul.26 | Aug.26 | Sep.26 | Oct.26 | Nov.26 | Dec.26 | Jan.27 | Feb.27 | Mar.27 | Apr.27 | May.27 | Jun.27 |  | Jul.27 | Aug.27 | Sep.27 | Oct.27 | Nov.27 | Dec.27 | Jan.28 |  | Feb.28 | Mar.28 | Apr.28 | May.28 | Jun.28 | Jul.28 | Aug.28 | Sep.28 | Oct.28 | Nov.28 | Dec.28 | Jan.29 | Feb.29 | Mar.29 | Apr.29 | May.29 | Jun.29 | Jul.29 | Aug.29 | Sep.29 | Oct.29 | Nov.29 | Dec.29
BOARD MEETINGS |  | Board+ conference |  |  |  | Board + LÍS |  |  | Board + RC + CF |  |  |  | Board + Ministry + Conference | [5 empty] | Board + LÍS |  | Board + RC + CF |  |  |  |  | Board + Ministry + Conference | [5 empty] | Board + LÍS |  | Board + RC + CF |  |  |  | Board + Ministry + Conference | [6 empty] | Board + LÍS |  | Board + RC + CF |  |  |  |  | Board + Ministry + Conference | [5 empty] | Board + LÍS |  | Board + RC + CF |  |  |  | Board + Ministry + Conference | [5 empty] | Board + LÍS |  | Board + RC + CF
RU |  | IWR planning dialogue |  |  | Enhancement topic approval | IBV | Appointing panel |  | Panel training | AQD | SER (25 FEB) | Panel preparations / Prep meeting with HEI |  | IWR (5-7 May) | Report writing |  |  |  | Report approval and publication |  |  | AQD | [12 empty] | AQD | [12 empty] | AQD | [5 empty] | IBV | [6 empty] | AQD | [11 empty] | AQD
UI | [10 empty] | AQD | [7 empty] | IBV |  | IWR planning dialogue (*combined institution UI and HU) |  | AQD | Enhancement topic approval |  | Appointing panel |  | Panel training | SER |  | Panel preparations / Prep meeting with HEI |  | IWR | Report writing |  | AQD |  | Report approval and publication | [10 empty] | AQD | [12 empty] | AQD |  |  |  | IBV
IUA | [9 empty] | AQD | [16 empty] | IWR planning dialogue | IBV | Enhancement topic approval |  |  | Appointing panel |  | Panel training | AQD | SER | Panel preparations / Prep meeting with HEI |  | IWR | Report writing |  |  |  |  | Report approval and publication |  |  | AQD | [12 empty] | AQD | [8 empty] | IBV |  |  | AQD
UNAK |  |  | AQD | [12 empty] | AQD | [12 empty] | AQD |  |  | IBV |  | IWR planning dialogue |  | Enhancement topic approval |  | Appointing panel |  | Panel training | AQD | SER |  | Panel preparations / Prep meeting with HEI |  | IWR | Report writing |  |  |  |  | Report approval and publication |  |  | AQD | [11 empty] | AQD
AUI | [9 empty] | AQD | [11 empty] | AQD | [12 empty] | AQD |  |  |  | IWR planning dialogue | IBV | Enhancement topic approval |  |  |  | Appointing panel |  | Panel training | AQD | SER |  | Panel preparations / Prep meeting with HEI |  | IWR | Report writing |  |  |  | Report approval and publication |  |  | AQD | [11 empty] | AQD
BU | [10 empty] | AQD | [11 empty] | AQD | [12 empty] | AQD | [8 empty] | IBV |  | IWR planning dialogue |  | AQD | Enhancement topic approval |  | Appointing panel |  | Panel training | SER |  | Panel preparations / Prep meeting with HEI |  | IWR | Report writing |  | AQD |  | Report approval and publication
ENQA | [8 empty] | SER production > |  | Appl request | [10 empty] | Submit SER | [5 empty] | ENQA review
OTHER | [5 empty] | NOQA |  | ENQA General assembly |  |  | Annual report |  |  | ENQA members forum |  |  |  |  | NOQA | ENQA General assembly |  |  | Annual report |  |  |  | ENQA members forum |  |  |  |  | NOQA | ENQA General assembly |  |  | Annual report |  |  | ENQA members forum | [5 empty] | NOQA | ENQA General assembly |  |  | Annual report |  |  |  | ENQA members forum |  |  |  |  | NOQA | ENQA General assembly |  |  | Annual report |  |  | ENQA members forum |  |  |  |  | NOQA | ENQA General assembly
IWR | Institution-wide review site visit
AQD | Annual quality dialogue (Secretariat)
IBV | Institutional Board visit
Board | Board meeting (+ conference/stakeholder meetings if stated)
Version history:
Version 4, September 2026: HU removed from document due to integration into University of Iceland