## Overview
Annex 10a: | QEF3 Timeline | [8 empty] | QB Board meeting 4-5 March 2024
Action: | For discussion
| Sp24 | Fa24 | Sp25 | Fa25 | Sp26 | Fa26 | Sp27 | Fa27 | Sp28 | Fa28 | Sp29 | Fa29
RU |  | AQD | IWR | AQD |  | AQD |  | AQD |  | AQD |  | AQD
HU |  |  | AQD | IWR | AQD |  | AQD |  | AQD |  | AQD
UI |  |  | AQD |  | AQD | IWR | AQD |  | AQD |  | AQD
IUA |  | AQD |  | AQD |  | AQD | IWR | AQD |  | AQD |  | AQD
UNAK |  |  | AQD |  | AQD |  | AQD | IWR | AQD |  | AQD
AUI |  | AQD |  | AQD |  | AQD |  | AQD | IWR
BU |  |  | AQD |  | AQD |  | AQD |  | AQD | IWR | AQD
IWR | Institution-wide review | [6 empty] | Possible mergers between HU + UI and BU + UNAK during the cycle
AQD | Annual quality dialogue (Secretariat) | [6 empty] | No IWRs in Spring 2026
IBV | Institutional Board visit (to be filled in during Board meeting)
ENQA Membership Application Timeline (suggestion)
Spring 2025 | Application request to ENQA (March/April)
2025 | SER production (all year)
Spring 2026 | Submission of the SER (February) (6 months before reivew visit)
Fall 2026 | Review visit (August/September)
ENQA guidelines specify that the review process may take 12-14 months from the first request by the agency to the completion of the procedure

## Month-by-month
OPR-0006 QEF3 Timeline
Operational Document
Version no. 3 / Date of Publication 12.01.2025
Responsible staff member: Executive Director
Reviewed: Annually
WHO | Apr.24 | May.24 | Jun.24 | Jul.24 | Aug.24 | Sep.24 |  | Oct.24 | Nov.24 | Dec.24 | Jan.25 | Feb.25 | Mar.25 | Apr.25 | May.25 |  | Jun.25 |  | Jul.25 | Aug.25 | Sep.25 | Oct.25 | Nov.25 | Dec.25 | Jan.26 |  | Feb.26 | Mar.26 | Apr.26 | May.26 | Jun.26 | Jul.26 | Aug.26 | Sep.26 | Oct.26 | Nov.26 | Dec.26 | Jan.27 | Feb.27 | Mar.27 | Apr.27 | May.27 | Jun.27 |  | Jul.27 | Aug.27 | Sep.27 | Oct.27 | Nov.27 | Dec.27 | Jan.28 |  | Feb.28 | Mar.28 | Apr.28 | May.28 | Jun.28 | Jul.28 | Aug.28 | Sep.28 | Oct.28 | Nov.28 | Dec.28 | Jan.29 | Feb.29 | Mar.29 | Apr.29 | May.29 | Jun.29 | Jul.29 | Aug.29 | Sep.29 | Oct.29 | Nov.29 | Dec.29
BOARD MEETINGS |  | Board+ conference |  |  |  | Board + LÍS |  |  | Board + RC + CF |  |  |  | Board + Ministry + Conference | [7 empty] | Board + LÍS |  | Board + RC + CF |  |  |  |  | Board + Ministry + Conference | [5 empty] | Board + LÍS |  | Board + RC + CF |  |  |  | Board + Ministry + Conference | [6 empty] | Board + LÍS |  | Board + RC + CF |  |  |  |  | Board + Ministry + Conference | [5 empty] | Board + LÍS |  | Board + RC + CF |  |  |  | Board + Ministry + Conference | [5 empty] | Board + LÍS |  | Board + RC + CF
RU |  | IWR planning dialogue |  |  | Enhancement topic approval | IBV | Appointing panel |  | Panel training | AQD | SER (25 FEB) | Panel preparations / Prep meeting with HEI |  | IWR (5-7 May) | Report writing | [5 empty] | Report approval and publication |  |  | AQD | [12 empty] | AQD | [12 empty] | AQD | [5 empty] | IBV | [6 empty] | AQD | [11 empty] | AQD
HU |  |  | AQD | [5 empty] | IWR planning dialogue |  | Enhancement topic approval |  | Appointing panel |  | IBV | Panel training | SER | AQD |  | Panel preparations / Prep meeting with HEI |  | IWR | Report writing |  |  |  |  | Report approval and publication |  |  | AQD | [11 empty] | AQD | [13 empty] | AQD |  |  | IBV | [8 empty] | AQD
UI | [10 empty] | AQD | [9 empty] | IBV |  | IWR planning dialogue (*combined institution UI and HU) |  | AQD | Enhancement topic approval |  | Appointing panel |  | Panel training | SER |  | Panel preparations / Prep meeting with HEI |  | IWR | Report writing |  | AQD |  | Report approval and publication | [10 empty] | AQD | [12 empty] | AQD |  |  |  | IBV
IUA | [9 empty] | AQD | [18 empty] | IWR planning dialogue | IBV | Enhancement topic approval |  |  | Appointing panel |  | Panel training | AQD | SER | Panel preparations / Prep meeting with HEI |  | IWR | Report writing |  |  |  |  | Report approval and publication |  |  | AQD | [12 empty] | AQD | [8 empty] | IBV |  |  | AQD
UNAK |  |  | AQD | [13 empty] | AQD | [13 empty] | AQD |  |  | IBV |  | IWR planning dialogue |  | Enhancement topic approval |  | Appointing panel |  | Panel training | AQD | SER |  | Panel preparations / Prep meeting with HEI |  | IWR | Report writing |  |  |  |  | Report approval and publication |  |  | AQD | [11 empty] | AQD
AUI | [9 empty] | AQD | [13 empty] | AQD | [12 empty] | AQD |  |  |  | IWR planning dialogue | IBV | Enhancement topic approval |  |  |  | Appointing panel |  | Panel training | AQD | SER |  | Panel preparations / Prep meeting with HEI |  | IWR | Report writing |  |  |  | Report approval and publication |  |  | AQD | [11 empty] | AQD
BU | [10 empty] | AQD | [13 empty] | AQD | [12 empty] | AQD | [8 empty] | IBV |  | IWR planning dialogue |  | AQD | Enhancement topic approval |  | Appointing panel |  | Panel training | SER |  | Panel preparations / Prep meeting with HEI |  | IWR | Report writing |  | AQD |  | Report approval and publication
ENQA | [8 empty] | SER production > |  | Appl request | [12 empty] | Submit SER | [5 empty] | ENQA review
OTHER | [5 empty] | NOQA |  | ENQA General assembly |  |  | Annual report |  |  | ENQA members forum | [6 empty] | NOQA | ENQA General assembly |  |  | Annual report |  |  |  | ENQA members forum |  |  |  |  | NOQA | ENQA General assembly |  |  | Annual report |  |  | ENQA members forum | [5 empty] | NOQA | ENQA General assembly |  |  | Annual report |  |  |  | ENQA members forum |  |  |  |  | NOQA | ENQA General assembly |  |  | Annual report |  |  | ENQA members forum |  |  |  |  | NOQA | ENQA General assembly
IWR | Institution-wide review site visit
AQD | Annual quality dialogue (Secretariat)
IBV | Institutional Board visit
Board | Board meeting (+ conference/stakeholder meetings if stated)